Garden City Park Water District

PWS ID No. NY2902825

Quarterly Deferral Update

**Update on Wellhead Treatment Progress, Potential Issues and Water Quality Update**

**Report Date: September, 2022 Facility: Plant 7/10 Prepared by: Michael Levy, Superintendent**

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone** | **Date** | **On Schedule (Y/N)**  **Or Completed** | **Notes and Comments** |
| Complete treatment piloting | N/A |  |  |
| Completed engineering report/submit for regulatory review | 11/19/2019 | Completed | Submitted to NYSDOH, Approved by NYSDOH on 6/10/2020 |
| Complete project design/submit for regulatory review | 01/15/2020 | Completed | Submitted to NYSDOH, Approved by NYSDOH on 6/10/2020  (including GAC for PFAS treatment and provisions for future AOP treatment) |
| Commence project  Construction | 5/22/2020 | Completed | Contract signing date |
| 50% project completion | 6/22/2020 | Completed |  |
| Other | 10/16/2020 |  | NCDOH / NYSDOH Approval of completed works to run GAC treatment to system |
| 100% project completion | Spring 2022 | On Schedule | Minor punch list items remaining |

|  |
| --- |
| **Potential issues / concerns /delays:**  Plant 7/10 is located on Shelter Rock Road in Roslyn. Treatment for PFOA is installed and operational. As of 10/16/2020 the plant is producing system water with levels of PFOS and PFOA below detectable limits. Winter weather has delayed the completion of the project, but treatment is in place and operational. Final site work is complete. Minor punch list items remaining. |
| **Water Quality Update –** See attached summary |